## Unix Patching Standard SOP
UNIX PATCHING STANDARD PLAYBOOK
Sr No | Task details | Team
1 | Take Operating Systsm configuration backup for servers which are scheduled under CR | Unix team
2 | Backup team to confirm the latest availability of OS/application data backup | Backup Team
3 | Incase of VM servers, take the snapshot of the server | Unix team/Wintel team
4 | Start the email communication, ensure that all the respective teams are part of email communication. Initiate the bridge and take roll call of teams which are required for the change | Unix team
5 | Disable the monitoring for the servers which are mentioned in the CR. Application team has to co-ordinate with MEM team to disable the probes. | MEM team
6 | Once the probes are disables, application team will stop the application. Application team will provide the servers list if they want to do it in rolling manner. | Application team
6 | Unix team will patch the servers using Ansible. | Unix team
7 | Post patching /Reboot, Unix team will perform post patching validation and inform application team to start/validate the application | Unix team
8 | Application/ DB team will perform the final validation and Start the application on requested servers only. | Application team
9 | Enable the monitoring on the servers | MEM team
10 | Send final communication to all stakeholder | Unix team

## Escalation Matrix
Escalation Matrix:
Technical Issue Matrix:
Follow the technical Issue Matrix immediately if there is any issue from technical end.
Leave the voice message if there is a miss in call pickup by anyone in the following matrix.
If the technical issue is not resolved, Update Joe Arko/Andrea and get confirmation whether the activity needs to be cancelled.
Escalation | Name | Phone Number | Timeframe
Primary Escalation - TCS Linux Team | Nitin Jain | 612 849 4817 | Immediately
| Vasudeo Sathe | 9523564809 | Immediately
| Sekhar Pulipati | 612 806 8353 | Immediately
Escalation - TCS Linux Team | Sridhar | 612 201 4839 | 30 Minute delay
Secondary Escalation- BBY Platform Services -Linux (Technical Issue) | Saul Alanis Sean Shore and Rob Caldwell | 612 839 4219, 763 412 8715,952 232 8192 | 60 Minute delay
Secondary Escalation- BBY Platform Services -Linux (For activity cancel decision) | Andrea Rucks /Joe | 612 812-4698, 612 306 6293 | 90 Minute delay
Application Team Response/Schedule Issue:
Follow the Schedule/Application Issue Escalation Matrix immediately after 30 minutes if there is no response from application Team.
Leave the voice message if there is a miss in call pickup by anyone in the following matrix.
If there is no response from BBY Escalation Team even after 60 minutes of voice mail, Unix team will cancel the CR.
Escalation | Name | Phone Number | Timeframe
Service Manager, PM -BBY Team | Joseph Arko / Anjali | 612 306 6293, 651 605 5826 | 30 Minute delay
Secondary Escalation- BBY Platform Services -Linux | Andrea Rucks | 612 812-4698 | 30 Minute delay

## RHEL 5 Packages
=============================================================================================
Package Arch Version
=============================================================================================
Updating:
Updating:
tw-eg-driver-rhel x86_64 1.3.458-1 BBY_Platform_BBY_RH5_BBY_RH5 1.7 M

## RHEL6 Packages
======================================================================================================
Package Arch Version
======================================================================================================
Installing:
kernel x86_64 2.6.32-696.18.7.el6 rhel-6-server-rpms 32 M
kernel-devel x86_64 2.6.32-696.18.7.el6 rhel-6-server-rpms 11 M
Updating:
kernel-firmware noarch 2.6.32-696.18.7.el6 rhel-6-server-rpms 29 M
kernel-headers x86_64 2.6.32-696.18.7.el6 rhel-6-server-rpms 4.5 M
microcode_ctl x86_64 1:1.17-25.4.el6_9 rhel-6-server-rpms 1.2 M
rubrik-agent x86_64 3.2.3-1.0 BBY_Platform_BBY_RH6_BBY_RH6 5.4 M
tw-eg-driver-rhel x86_64 1.3.458-1 BBY_Platform_BBY_RH6_BBY_RH6 1.7 M
Removing:
kernel x86_64 2.6.32-696.1.1.el6 @rhel-6-server-rpms 131 M
kernel-devel x86_64 2.6.32-696.1.1.el6 @rhel-6-server-rpms 26 M

## RHEL7 Packages
=======================================================================================================
Package Arch Version
=======================================================================================================
========================================================================================================================================================================
Package Arch Version Repository Size
========================================================================================================================================================================
Installing:
kernel x86_64 3.10.0-693.11.6.el7 rhel-7-server-rpms 43 M
Updating:
dracut x86_64 033-502.el7_4.1 rhel-7-server-rpms 321 k
dracut-config-rescue x86_64 033-502.el7_4.1 rhel-7-server-rpms 56 k
dracut-network x86_64 033-502.el7_4.1 rhel-7-server-rpms 98 k
kernel-tools x86_64 3.10.0-693.11.6.el7 rhel-7-server-rpms 5.1 M
kernel-tools-libs x86_64 3.10.0-693.11.6.el7 rhel-7-server-rpms 5.1 M
linux-firmware noarch 20170606-58.gitc990aae.el7_4 rhel-7-server-rpms 35 M
microcode_ctl x86_64 2:2.1-22.5.el7_4 rhel-7-server-rpms 786 k
python-perf x86_64 3.10.0-693.11.6.el7 rhel-7-server-rpms 5.1 M
tw-eg-driver-rhel x86_64 1.3.458-1 BBY_Platform_RHEL7_BBY_RHEL7_BBY 1.7 M