## PLDR RLQ35-36XDB 7-30 to 7-31 (hidden)
Milestones | Start Date | End Date | ETS (CST) | ETC (CST) | Activity | Team Responsible for the Changes | Est. Time Needed | Status | Actual Time Started | Actual Time Completed | Delays Experienced / Comments | Notes
DAY BEFORE STEPS |  |  |  |  | Take one-off full system backup on 7/29, retention of 7 days | Backup Team
[5 empty] | Ensure database backup is good on 7/29 | Database Team
[5 empty] | Ensure /var has 650 MB free space | Unix Team
[5 empty] | CBG Environment Team to provide ESM Team with list of Monitoring Probes scheduled for maintenance on 7/29. | CBG Environment Team
Pre-Deployment Steps | 2013-07-30 | 2013-07-31 | 23:00 | 5:00 | RHEL 5 ORACLE RAC and MySQLServers in-Scope for PCI PROD-LIKE patching: BBfB / MyHR / TLC / WhiteLabel / SAMI / Home Connections / Scheduling / Tools Front-End DB CLUSTER (RLQ35XDB RLQ36XDB)
1a | 2013-07-30 | 2013-07-30 | 23:00 | 23:20 | STOP monitoring and alerting of all servers in DB CLUSTER (RLQ35XDB RLQ36XDB), (SERVERS DONE IN PARALLEL) (CONCURRENT with 1b 1c 1d) | ESM Team | 20 minutes
1b | 2013-07-30 | 2013-07-30 | 23:00 | 23:20 | BACKUP server configuration backup of all servers in DB CLUSTER (RLQ35XDB RLQ36XDB) (SERVERS DONE IN PARALLEL) (CONCURRENT with 1a 1c 1d) | Unix Team | 20 minutes
1c | 2013-07-30 | 2013-07-30 | 23:00 | 23:20 | TLC: Cancel the job stream "PRETEND PROD-LIKE JOBSTREAM" only after the confirmation via TLC support team. (CONCURRENT with 1a 1b 1d) | Data Center Ops OFF-SHORE / TLC Team | 20 minutes | Piyush
1d | 2013-07-30 | 2013-07-30 | 23:00 | 23:20 | DOWNLOAD RPM's for Oracle ASM LIB to DB CLUSTER (RLQ35XDB RLQ36XDB). Database Team to communicate location of RPM package to UNIX Team (UNIX team will manually install Oracle ASM LIB RPM when applying patches in step 6). (CONCURRENT with 1a 1b 1c). | Database Team / Unix Team | 20 minutes
2a | 2013-07-30 | 2013-07-30 | 23:20 | 23:35 | VALIDATE that no application batch jobs are running and cancel jobs if they are (ALL APPLICATIONS DONE IN PARALLEL) (CONCURRENT with 2b 2c) | DC Ops | 15 minutes
2b | 2013-07-30 | 2013-07-30 | 23:20 | 23:35 | STOP Beantstalk from WhiteLabel ADMIN PAGE. (CONCURRENT with 2a 2c) | CBG Environment Team | 15 minutes
2c | 2013-07-30 | 2013-07-30 | 23:20 | 23:35 | ENABLE MAINTENANCE PAGE for WhiteLabel and Tools Front-END from the WhiteLabel / Tools Front-End PROD-LIKE App Servers. (CONCURRENT with 2a 2b) | ASM Infra Team / CBG Environment Team | 15 minutes
3a | 2013-07-30 | 2013-07-31 | 23:35 | 0:25 | STOP BBFB and VALIDATE that application is down. (DONE IN PARALLEL on BBFB servers) (CONCURRENT with 3b and 3c) | BBFB Team | 50 minutes
3b | 2013-07-30 | 2013-07-31 | 23:35 | 0:25 | STOP SAMI, White Label, Home Connections, Tools Front-End and Scheduling applications. (DONE IN PARALLEL) (ASM Infra Team to notify CBG Environment Team as each application is stopped to allow them to validate immediately after, SYNCHRONIZED with step 3c) (CONCURRENT with 3a) | ASM INFRA Team / Need 2 ASM Infra admins | 50 minutes | Who are the off-shroe admins? MW to provide
3c | 2013-07-30 | 2013-07-31 | 23:35 | 0:25 | VALIDATE SAMI, WhiteLabel, Home Connections, Tools Front-End, and Scheduling are stopped. (Work alongside ASM Infra Team as they stop each application, perform validation immediately afterwards that application is stopped, SYNCHRONIZED with step 3b) (CONCURRENT with 3a) | CBG Environment Team / Need 2 CBG admins | 50 minutes | Off-shore Names to be provided
4 | 2013-07-31 | 2013-07-31 | 0:25 | 0:40 | STOP all MySQL on DB CLUSTER (RLQ35XDB RLQ36XDB) (DONE IN PARALLEL ON EACH DB SERVER) | Database Team | 15 minutes
5 | 2013-07-31 | 2013-07-31 | 0:40 | 1:10 | STOP all Oracle DB CLUSTER (RLQ35XDB RLQ36XDB) (DONE IN PARALLEL ON EACH DB SERVER) | Database Team | 30 minutes
6 | 2013-07-31 | 2013-07-31 | 1:10 | 2:00 | SIMULATE / PRETEND / DON'T REALLY PATCH RHEL 5 patching physical servers and PRETEND TO manually apply Oracle ASM LIB RPM previously provided by Oracle DB Team in step 1 on DB CLUSTER (RLQ35XDB RLQ36XDB) (SERVERS DONE IN PARALLEL) | Unix Team | 50 minutes
7 | 2013-07-31 | 2013-07-31 | 2:00 | 2:30 | REBOOT servers and VALIDATE physical servers on DB CLUSTER (RLQ35XDB RLQ36XDB) (SERVERS REBOOTED IN PARALLEL - DON'T DO THEM SERIALLY FOR BEST RESULTS) | Unix Team | 30 minutes
8 | 2013-07-31 | 2013-07-31 | 2:30 | 3:05 | VERIFY the Oracle ASM LIB and Disk integrity DB CLUSTER (RLQ35XDB RLQ36XDB). (DONE ON BOTH SERVERS IN PARALLEL) | Database Team | 35 Minutes
9a | 2013-07-31 | 2013-07-31 | 3:05 | 3:45 | VALIDATE that Oracle RAC, Protegrity Clients, are running on DB CLUSTER (RLQ35XDB RLQ36XDB). (DONE IN PARALLEL ON EACH SERVER) (CONCURRENT with 9b) | Database Team / ORACLE admin | 40 Minutes
9b | 2013-07-31 | 2013-07-31 | 3:05 | 3:45 | VALIDATE that MySQL VIP's and MySQL are running on DB CLUSTER (RLQ35XDB RLQ36XDB). (DONE IN PARALLEL ON EACH SERVER) (CONCURRENT with 9a) | Database Team / MySQL admin | 40 Minutes
10a | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | START BBFB and validate that application is running. (CONCURRENT with 10b 10c 10d 10e 10f) | BBFB Team | 55 minutes
10b | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | DISABLE MAINTENANCE PAGE for WhiteLabel and Tools Front-END from the WhiteLabel / Tools Front-End PROD-LIKE App Servers. (CONCURRENT with 10a 10c 10d 10e 10f) | ASM INFRA Team / Need 2 Infra admins | 55 minutes
10c | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | START SAMI, White Label, Home Connections and Tools Front-End applications. (APPS STARTED IN PARALLEL) (ASM Infra Team to notify CBG Environment Team as each application is started to allow them to validate immediately after, SYNCHRONIZED with step 10d, CONCURRENT with 10a 10b 10e 10f) | ASM INFRA Team / Need 2 Infra admins | 55 minutes
10d | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | VALIDATE if SAMI, White Label, Home Connections and Tools Front-End applications are running. (CBG Environment Team to work alongside ASM Infra Team as they start each application, perform validation immediately afterwards that application is started, SYNCHRONIZED with step 10c, CONCURRENT with 10a 10b 10d 10e 10f) | CBG Environment Team / Need 2 CBG admins | 55 minutes
10e | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | START Beanstalk from WhiteLabel PROD-LIKE server admin page. (CBG Environment Team to work alongside ASM Infra Team as they start each application, perform validation immediately afterwards that application is started, SYNCHRONIZED with step 10d, CONCURRENT with 10a 10b 10c 10e 10f) | CBG Environment Team / Need 2 CBG admins | 55 minutes
10f | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | VALIDATE TLC applications are running correctly. They should automatically reconnect to the Oracle database when it is back online. (CONCURRENT with 10a 10b 10c 10d 10e) | TLC | 55 minutes
11a | 2013-07-31 | 2013-07-31 | 4:40 | 5:00 | START monitoring and alerting of all Servers DB CLUSTER 1 (DLP20XDB DLP21XDB DLP22XDB), (SERVERS DONE IN PARALLEL) (CONCURRENT with 11b) | ESM Team | 20 minutes
11b | 2013-07-31 | 2013-07-31 | 4:40 | 5:00 | TLC JOBS: RESTART JOB STREAM???? PIYUSH TO CONFIRM???? (CONCURRENT with 11a) | Data Center Ops OFF-SHORE / TLC Team | 20 minutes | Piyush
Milestone 1: PROD-LIKE DB Instances BBfB / MyHR / TLC / WhiteLabel / SAMI / Home Connections / Scheduling / Tools Front-End |  | 2013-07-31 |  | 5:00 | PROD-LIKE DB CLUSTER (RLQ35XDB and RLQ36XDB), is PCI PATCHED |  | 0 minute buffer

## PROD DLP20-21-22XDB NEW (hidden)
Milestones | Start Date | End Date | ETS (CST) | ETC (CST) | Activity | Team Responsible for the Changes | Est. Time Needed | Status | Actual Time Started | Actual Time Completed | Delays Experienced / Comments | Notes
DAY BEFORE STEPS |  |  |  |  | Take one-off full system backup on 7/29, retention of 7 days | Backup Team
[5 empty] | Ensure database backup is good on 7/29 | Database Team
[5 empty] | Ensure /var has 650 MB free space | Unix Team
[5 empty] | CBG Environment Team to provide ESM Team with list of Monitoring Probes scheduled for maintenance on 7/29. | BEAST Mobile Support Team
Pre-Deployment Steps | 2013-07-30 | 2013-07-31 | 23:00 | 5:00 | RHEL 5 ORACLE RAC and MySQLServers in-Scope for PCI PROD patching: BBfB / MyHR / TLC / WhiteLabel / SAMI / Home Connections / Scheduling / Tools Front-End DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB)
1a | 2013-07-30 | 2013-07-30 | 23:00 | 23:20 | STOP monitoring and alerting of all servers in DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB). (SERVERS DONE IN PARALLEL) (CONCURRENT with 1b 1c 1d) | ESM Team | 20 minutes
1b | 2013-07-30 | 2013-07-30 | 23:00 | 23:20 | BACKUP server configuration backup of all servers in DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB) (SERVERS DONE IN PARALLEL) (CONCURRENT with 1a 1c 1d) | Unix Team | 20 minutes
1c | 2013-07-30 | 2013-07-30 | 23:00 | 23:20 | TLC: Cancel the job stream "P02INMS01#WBNLD097" only after confirmation by TLC support team. (CONCURRENT with 1a 1b 1d) | Data Center Ops OFF-SHORE / TLC Team | 20 minutes | Piyush
1d | 2013-07-30 | 2013-07-30 | 23:00 | 23:20 | DOWNLOAD RPM's for Oracle ASM LIB to DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB). Database Team to communicate location of RPM package to UNIX Team (UNIX team will manually install Oracle ASM LIB RPM when applying patches in step 6). (CONCURRENT with 1a 1b 1c) | Database Team / Unix Team | 20 minutes
2a | 2013-07-30 | 2013-07-30 | 23:20 | 23:35 | VALIDATE that no application batch jobs are running and cancel jobs if they are (ALL APPLICATIONS DONE IN PARALLEL) (CONCURRENT with 2b 2c) | DC Ops | 15 minutes
2b | 2013-07-30 | 2013-07-30 | 23:20 | 23:35 | STOP Beantstalk from WhiteLabel ADMIN PAGE. (CONCURRENT with 2a 2c) | CBG Environment Team | 15 minutes
2c | 2013-07-30 | 2013-07-30 | 23:20 | 23:35 | ENABLE MAINTENANCE PAGE for WhiteLabel and Tools Front-END from the WhiteLabel / Tools Front-End PROD-LIKE App Servers. (CONCURRENT with 2a 2b) | ASM Infra Team / CBG Environment Team | 15 minutes
3a | 2013-07-30 | 2013-07-31 | 23:35 | 0:25 | STOP BBFB and VALIDATE that application is down. (DONE IN PARALLEL on BBFB Servers) (CONCURRENT with 3b and 3c) | BBFB Team | 50 minutes
3b | 2013-07-30 | 2013-07-31 | 23:35 | 0:25 | STOP SAMI, White Label, Home Connections, Tools Front-End and Scheduling applications. (DONE IN PARALLEL) (ASM Infra Team to notify CBG Environment Team as each application is stopped to allow them to validate immediately after, SYNCHRONIZED with step 3c) (CONCURRENT with 3a) | ASM INFRA Team / Need 2 Infra admins | 50 minutes | Who are the off-shroe admins? MW to provide
3c | 2013-07-30 | 2013-07-31 | 23:35 | 0:25 | VALIDATE SAMI, WhiteLabel, Home Connections, Tools Front-End, and Scheduling are stopped. (Work alongside ASM Infra Team as they stop each application, perform validation immediately afterwards that application is stopped, SYNCHRONIZED with step 3b) (CONCURRENT with 3a) | CBG Environment Team / Need 2 CBG admins | 50 minutes | Off-shore Names to be provided
4 | 2013-07-31 | 2013-07-31 | 0:25 | 0:40 | STOP all MySQL on DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB) (DONE IN PARALLEL ON EACH DB SERVER) | Database Team | 15 minutes
5 | 2013-07-31 | 2013-07-31 | 0:40 | 1:10 | STOP all Oracle DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB) (DONE IN PARALLEL ON EACH DB SERVER) | Database Team | 30 minutes
6 | 2013-07-31 | 2013-07-31 | 1:10 | 2:00 | START PATCHING RHEL 5 physical servers and MANUALLY apply Oracle ASM LIB RPM previously provided by Oracle DB Team in step 1d on DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB) (SERVERS DONE IN PARALLEL) | Unix Team | 50 minutes
7 | 2013-07-31 | 2013-07-31 | 2:00 | 2:30 | REBOOT servers and VALIDATE physical servers on DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB) (SERVERS REBOOTED IN PARALLEL - DON'T DO THEM SERIALLY FOR BEST RESULTS) | Unix Team | 30 minutes
8 | 2013-07-31 | 2013-07-31 | 2:30 | 3:05 | VERIFY the Oracle ASM LIB and Disk integrity DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB). (DONE ON BOTH SERVERS IN PARALLEL) | Database Team | 35 Minutes
9a | 2013-07-31 | 2013-07-31 | 3:05 | 3:45 | VALIDATE that Oracle RAC, Protegrity Clients, are running on DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB). (DONE IN PARALLEL ON EACH SERVER) (CONCURRENT with 9b) | Database Team / ORACLE admin | 40 Minutes
9b | 2013-07-31 | 2013-07-31 | 3:05 | 3:45 | VALIDATE that MySQL VIP's and MySQL are running on DB CLUSTER( DLP20XDB DLP21XDB DLP22XDB). (DONE IN PARALLEL ON EACH SERVER) (CONCURRENT with 9a) | Database Team / MySQL admin | 40 Minutes
10a | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | START BBFB and validate that application is running. (CONCURRENT with 10b 10c 10d 10e 10f) | BBFB Team | 55 minutes
10b | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | DISABLE MAINTENANCE PAGE for WhiteLabel and Tools Front-END from the WhiteLabel / Tools Front-End PROD-LIKE App Servers. (CONCURRENT with 10a 10c 10d 10e 10f) | ASM INFRA Team / Need 2 Infra admins | 55 minutes
10c | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | START SAMI, White Label, Home Connections and Tools Front-End applications. (APPS STARTED IN PARALLEL) (ASM Infra Team to notify CBG Environment Team as each application is started to allow them to validate immediately after, SYNCHRONIZED with step 10d, CONCURRENT with 10a 10b 10e 10f) | ASM INFRA Team / Need 2 Infra admins | 55 minutes
10d | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | VALIDATE if SAMI, White Label, Home Connections and Tools Front-End applications are running. (CBG Environment Team work alongside ASM Infra Team as they start each application, perform validation immediately afterwards that application is started, SYNCHRONIZED with step 10c, CONCURRENT with 10a 10b 10d 10e 10f) | CBG Environment Team / Need 2 CBG admins | 55 minutes
10e | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | START Beanstalk from WhiteLabel PROD server admin page. (CBG Environment Team work alongside ASM Infra Team as they start each application, perform validation immediately afterwards that application is started, SYNCHRONIZED with step 10d, CONCURRENT with 10a 10b 10c 10e 10f) | CBG Environment Team / Need 2 CBG admins | 55 minutes
10f | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | VALIDATE MyHR and TLC applications are running correctly. They should automatically reconnect to the Oracle database when it is back online. (CONCURRENT with 10a 10b 10c 10d 10e) (Unix Team / MyHR: open browser, click on PROD-LIKE hr.bestbuy.com URL try to login with aID and netowkr login for MyHR validation, escalate to Balaram from MyHR in Contact Info Tab if there is an issue) | TLC / Unix Team assisting MyHR | 55 minutes | NEED PROD-LIKE hr.bestbuy.com URL
11a | 2013-07-31 | 2013-07-31 | 4:40 | 5:00 | START monitoring and alerting of all Servers DB CLUSTER 1 (DLP20XDB DLP21XDB DLP22XDB), (SERVERS DONE IN PARALLEL) (CONCURRENT with 11b) | ESM Team | 20 minutes
11b | 2013-07-31 | 2013-07-31 | 4:40 | 5:00 | TLC JOBS: RESTART JOB STREAM???? ???? (CONCURRENT with 11a) | Data Center Ops OFF-SHORE / TLC Team | 20 minutes | Piyush
Milestone 1: PROD DB Instances BBfB / MyHR / TLC / WhiteLabel / SAMI / Home Connections / Scheduling / Tools Front-End |  | 2013-07-31 |  | 5:00 | PROD DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB) is PCI PATCHED |  | 0 minute buffer

## DEV DLD55-56DB (hidden)
Milestones | Start Date | End Date | ETS (CST) | ETC (CST) | Activity | Team Responsible for the Changes | Est. Time Needed | Status | Actual Time Started | Actual Time Completed | Delays Experienced / Comments | Notes
Pre-Deployment Steps | 2013-09-04 | 2013-09-04 | 15:30 |  | DEV DB CLUSTER ORACLE RAC Servers in-Scope: (DLD55DB DLD56DB)
1a | 2013-09-04 | 2013-09-04 | 15:30 | 15:45 | STOP monitoring and alerting of all Servers (CONCURRENT with 1b) DB CLUSTER (DLD55DB DLD56DB) (servers done in parallel). | ESM Team | 15 minutes | Kamal Dadala
1b | 2013-09-04 | 2013-09-04 | 15:30 | 15:45 | Take server configuration backup of all servers (CONCURRENT with 1a) DB CLUSTER (DLD55DB DLD56DB) (servers done in parallel) | Unix Team | 15 minutes | Sudhakar / Dipak
1c | 2013-09-04 | 2013-09-04 | 15:30 | 15:45 | VALIDATE that no TRANSFER ORDERS (TO) application batch jobs are running and per Lynn Canama, pause them | RMS Support Team | 15 minutes | *IS Retek Staff
| 2013-09-04 | 2013-09-04 | 15:30 | 15:45 | VALIDATE that INVENTORY AVAILABILITY and ORDER SOURCING services are stopped | OMS Support Team | 15 minutes | *ASMEOMS
2 | 2013-09-04 | 2013-09-04 | 15:45 | 16:15 | STOP Oracle databases, VIPs and the Oracle Clusterware Services, VALIDATE status of ASM Disk Groups on DEV DB CLUSTER (DLD55DB DLD56DB), (DONE IN PARALLEL ON EACH DB CLUSTER) | Database Team | 20 minutes | Praveen
3 | 2013-09-04 | 2013-09-04 | 16:15 | 17:15 | APPLY Kernel parameter changes to /etc/sysctl.conf, add the deadline scheduler to /boot/grub/grub.conf, apply network driver updates and changes to /etc/modprobe.conf, comment out /u01 in /etc/fstab, and network firmware updates. REBOOT for DEV DB CLUSTER (DLD55DB DLD56DB) (DONE IN PARALLEL ON EACH SERVER) | Unix Team | 60 minutes | Sudhakar / Dipak
4 | 2013-09-04 | 2013-09-04 | 17:15 | 17:30 | VALIDATE OS is running fine, uncomment /u01 in /etc/fstab and manually mount without fsck for DEV DB CLUSTER (DLD55DB DLD56DB) (DONE IN PARALLEL ON EACH SERVER) | Unix Team | 15 minutes | Sudhakar / Dipak
5 | 2013-09-04 | 2013-09-04 | 17:30 | 18:15 | START / VALIDATE ASM Disk Groups are mounted. VALIDATE Oracle Clusterware, Oracle databases and services have started (done via /etc/inittab) on DB CLUSTER (DLD55DB DLD56DB) (DONE IN PARALLEL ON EACH SERVER) | Database Team | 60 Minutes | Praveen
6a | 2013-09-04 | 2013-09-04 | 18:15 | 18:45 | VALIDATE RETEK applications started correctly and are accessing database services and that any TRANSFER ORDERS (TO) are unpaused / released for DEV DB CLUSTER (DLD55DB DLD56DB) (CONCURRENT with 6b) | RMS Support Team | 30 Minutes | IS Retek Staff
6b | 2013-09-04 | 2013-09-04 | 18:15 | 18:45 | VALIDATE that INVENTORY AVAILABILITY and ORDER SOURCING services are started (CONCURRENT with 6a) | OMS Support Team | 30 minutes | ASMEOMS
7 | 2013-09-04 | 2013-09-04 | 18:45 | 19:00 | START monitoring and alerting of all servers in DEV DB CLUSTER (DLD55DB DLD56DB) (DONE IN PARALLEL FOR EACH SERVER) | ESM Team | 15 minutes
Milestone 1: DB Cluster RETEK / Oracle EBS / Discover | 2013-09-04 | 2013-09-04 |  | 19:00 | DEV DB CLUSTER SERVERS, DLD55DB and DLD56DB, are updated with Red Hat and HP recommendations

## PROD pdl01gendb22 DAY 1
Milestones | Start Date | End Date | ETS (CST) | ETC (CST) | Activity | Team Responsible for the Changes | Est. Time Needed | OWNER | Actual Time Started | Actual Time Completed | Delays Experienced / Comments | Notes
DAY BEFORE STEPS |  |  |  |  | Take one-off full system backup , retention of 7 days | Backup Team
[5 empty] | Ensure database backup is good | Database Team
[5 empty] | Ensure / 400 and /var has 200 MB free space | Unix Team
PRE-DEPLOYMENT STEPS | 2017-05-07 | 2017-05-07 | 14:00 | 15:00 | PROD DB CLUSTER ORACLE RAC Servers in-Scope: (pdl01gendb022)
0 | 2017-05-07 | 2017-05-07 | 14:00 | 15:00 | Load the Retek RTKOUT6 calendar | Maestro Team | 60 minutes | L2-TWS-IT-US
PATCH DEPLOYMENT STEPS | 2017-05-08 | 2017-05-08 | 4:05 | 10:00 | PROD DB CLUSTER ORACLE RAC Servers in-Scope: (pdl01gendb022)
1a.a | 2017-05-08 | 2017-05-08 | 4:05 | 4:10 | If any background jobs/process owned by rtkbatch user found needs to be killed at Unix level in DXP22/23HXA (Capture the snapshot of the jobs before killing if any) | RMS Support Team | 5 minutes | L2-ASM-RETEK-IT-US
1a.b | 2017-05-08 | 2017-05-08 | 4:10 | 4:20 | Killing the batch/job processes: a. DB level - RMS support to provide SID, SERIAL details to Oracle Apps DB team for killing in DB backend. b. OS level - If batch session is not connected to DB, RMS support to proceed in killing the session in OS level in Unix. | RMS Support Team / Oracle Apps Team | 10 minutes | L2-ASM-RETEK-IT-US / L2-DB-ORACLE-APPS-IT-GLB
1b | 2017-05-08 | 2017-05-08 | 4:05 | 4:20 | STOP monitoring and alerting of all Servers PROD DB CLUSTER (Pdl01gendb022 ) . STOP monitoring and alerting of all Servers PROD DB CLUSTER pdl01gendb023 ) . Refer the tab Probes for more details | Event Management team | 15 minutes | L1-MEM-IT-GLB
2a | 2017-05-08 | 2017-05-08 | 4:20 | 4:30 | Relocate Retek services from pdl01gendb022 to pdl01gendb023 using script "Day1prePCI_prod" Note: Script can be run from any location in pdl01gendb022 | L2 Oracle DBA Team | 10 minutes | L2-DB-ORACLE-IT-GLB
2b | 2017-05-08 | 2017-05-08 | 4:30 | 4:35 | Validate all Retek database services should be running on pdl01gendb023 Command: ostat -s op01rtdb | L2-Oracle-AppsDBA-Support | 5 minutes | L2-DB-ORACLE-APPS-IT-GLB
3a | 2017-05-08 | 2017-05-08 | 4:35 | 4:50 | Recycle the inventory management App Pool - One Server at a time pdw04b49ap001 pdw04b49ap002 pdw04b49ap003 pdw01b50ap01a pdw01b50ap02a pdw01b50ap02b | Layer 7 Team | 15 minutes | L2-MW-SOA-IT-GLB
3b |  |  | 4:35 | 4:50 | Apptalk needs to recycle all Real time adapters that are connecting to RETEK DB (RESA interface) | Apptalk Team | 15 minutes | L2-APPTALK
4a | 2017-05-08 | 2017-05-08 | 4:35 | 5:05 | Application team to validate their online screens are up and Manually run a test job in the backend. Confirm with the OMS team that OMS webservice is also running normally. | RMS Support Team | 30 minutes | L2-ASM-RETEK-IT-US
4b | 2017-05-08 | 2017-05-08 | 4:35 | 5:05 | All RSS containers need to be bounced one server at a time (Only if errors encountered while validating RSS) | L2-Oracle-AppsDBA-Support | 30 minutes | L2-DB-ORACLE-APPS-IT-GLB
4c | 2017-05-08 | 2017-05-08 | 4:35 | 5:05 | OMS Services need to be recycled only if RMS connectivity errors encountered, one server at a time | ASM Infra, Layer 7 and OMS Support Team | 30 minutes | L2-MW-APP-IT-GLB L2-ASM-OMS-IT-US
6a | 2017-05-08 | 2017-05-08 | 5:05 | 5:25 | Set the Limit for P01RTMS01 back to 30 Monitor whether batches are completing without failure | Datacenter Team | 20 minutes | L2-DATACENTER-OPS-IT-GLB
6b | 2017-05-08 | 2017-05-08 | 5:25 | 5:40 | If there were no issues encountered with the batch, set the limit back to 90. | Datacenter Team | 15 minutes | L2-DATACENTER-OPS-IT-GLB
6c | 2017-05-08 | 2017-05-08 | 5:25 | 5:40 | If there were no issues encountered with the batch, rerun the jobs killed at step 1.b | RMS Support Team | 15 minutes | L2-ASM-RETEK-IT-US
7a | 2017-05-08 | 2017-05-08 | 5:05 | 5:25 | DOWNLOAD RPM's for Oracle ASM LIB to DB CLUSTER (pdl01gendb022). Database Team to communicate location of RPM package to UNIX Team (UNIX team will manually install Oracle ASM LIB RPM when applying patches in step 6). (CONCURRENT with 1b 1c 1d)-If required | Database Team / Unix Team | 20 minutes | DBA Team / L2 Unix | Please doble check if there is any job running in pdl01gendb022
7b | 2017-05-08 | 2017-05-08 | 5:05 | 5:25 | BACKUP server configuration of all servers (CONCURRENT with 1a 1c 1d) PROD DB CLUSTER (pdl01gendb022) | Unix Team | 20 minutes | L2 Unix
7c |  |  | 5:05 | 5:35 | Stop NEW RSS instance on PDL01RSSWB01A, PDL01RSSWB02A and PDL01RSSAP01A and PDL01RSSAP02A Stop REIM Services on PDL01RM1AP02C and PDL01RM1AP03C | Appserver team | 30 minutes | L2-MW-APP-IT-GLB
7c | 2017-05-08 | 2017-05-08 | 5:05 | 5:35 | STOP Oracle database instance, VIPs and the Oracle Clusterware Services, VALIDATE status of ASM Disk Groups on PROD DB CLUSTER (pdl01gendb022) Disable crs on pdl01gendb022 | Database Team | 30 minutes | L2-DB-ORACLE-IT-US
8 | 2017-05-08 | 2017-05-08 | 5:35 | 6:35 | START PATCHING RHEL 5 physical servers on DB CLUSTER ( pdl01gendb022) PDL01RM1AP02C PDL01RM1AP03C PDL01RSSWB01A PDL01RSSWB02A PDL01RSSAP01A PDL01RSSAP02A | Unix Team | 60 minutes | L2-PLT-UNIX-IT-US
9 | 2017-05-08 | 2017-05-08 | 6:35 | 6:45 | VALIDATE OS is running fine, | Unix Team | 10 minutes | L2-PLT-UNIX-IT-US
10 | 2017-05-08 | 2017-05-08 | 6:45 | 7:45 | REBOOT servers and VALIDATE physical servers on DB CLUSTER pdl01gendb022 | Unix Team | 60 minutes | L2-PLT-UNIX-IT-US
11a | 2017-05-08 | 2017-05-08 | 7:45 | 9:00 | Enable crs in pdl01gendb022 and relink Oracle grid binaries Relink Oracle Home | Database Team | 75 minutes | L2-DB-ORACLE-IT-US
11b |  |  | 7:45 | 9:00 | Start NEW RSS instance on PDL01RSSWB01A and PDL01RSSAP02A. Start REIM Services on PDL01RM1AP02C and PDL01RM1AP03C | Appserver team | 75 minutes | L2-MW-
12 | 2017-05-08 | 2017-05-08 | 9:00 | 9:30 | START / VALIDATE ASM Disk Groups are mounted. VALIDATE Oracle Clusterware, Oracle database instances and VIP services have started (done via /etc/inittab) on DB CLUSTER (pdl01gendb022 ) op01rtdb01 (instance 01) should be UP/AVAILABLE by 11AM as ECB jobs is connecting to this RETEK DB instance. | Database Team | 30 minutes | L2-Oracle-Support | Confirm with OMS team if the web service required to be bounced after the PCI Patching ( If so than Layer7 team can do that )
12a | 2017-05-08 | 2017-05-08 | 9:45 | 10:00 | START SERVER monitoring and alerting pdl01gendb022 | ESM Team | 15 minutes | L1-MEM-IT-GLB
Milestone 1: PROD DB Cluster RETEK / Oracle EBS / Discover | 2017-05-08 | 2017-05-08 | 4:05 | 10:00 | PROD DB CLUSTER SERVERS, pdl01gendb022 are updated with latest Patches

## PRD DLP20-21-22XDB (hidden)
Milestones | Start Date | End Date | ETS (CST) | ETC (CST) | Activity | Team Responsible for the Changes | Est. Time Needed | Status | Actual Time Started | Actual Time Completed | Delays Experienced / Comments | Notes
DAY BEFORE STEPS |  |  |  |  | Take one-off full system backup on 7/29, retention of 7 days | Backup Team
[5 empty] | Ensure database backup is good on 7/29 | Database Team
[5 empty] | Ensure /var has 650 MB free space | Unix Team
[5 empty] | BEAST Mobile Support Team to provide ESM Team with list of Monitoring Probes scheduled for maintenance on 7/29. | BEAST Mobile Support Team
Pre-Deployment Steps | 2013-07-30 | 2013-07-31 | 23:00 | 5:00 | RHEL 5 ORACLE RAC and MySQLServers in-Scope for PCI PROD patching: BBfB / MyHR / TLC / WhiteLabel / SAMI / Home Connections / Scheduling / Tools Front-End DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB)
1a | 2013-07-30 | 2013-07-30 | 23:00 | 23:20 | STOP monitoring and alerting of all Servers (CONCURRENT with 1b 1c 1d) DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB), (SERVERS DONE IN PARALLEL) | ESM Team | 20 minutes
1b | 2013-07-30 | 2013-07-30 | 23:00 | 23:20 | Take server configuration backup of all servers (CONCURRENT with 1a 1c 1d) DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB) (SERVERS DONE IN PARALLEL) | Unix Team | 20 minutes
1c | 2013-07-30 | 2013-07-30 | 23:00 | 23:20 | TLC: Cancel the job stream P02INMS01#WBNLD097 only after the confirmation via TLC support team. (CONCURRENT with 1a 1b 1d) | Data Center Ops OFF-SHORE / TLC Team | 20 minutes
1d | 2013-07-30 | 2013-07-30 | 23:00 | 23:20 | DOWNLOAD RPM's for Oracle ASM LIB to DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB). Database Team to communicate location of RPM package to UNIX Team (UNIX team will manually install Oracle ASM LIB RPM when applying patches in step 5). (CONCURRENT with 1a 1b 1c). | Database Team | 20 minutes
2 | 2013-07-30 | 2013-07-30 | 23:20 | 23:35 | VALIDATE that no application batch jobs are running and cancel jobs if they are (ALL APPLICATIONS DONE IN PARALLEL) | DC Ops | 15 minutes
3a | 2013-07-30 | 2013-07-31 | 23:35 | 0:25 | STOP BBFB and validate that application is down. (DONE IN PARALLEL) (Concurrent with 3b and 3c) | BBFB Team | 50 minutes
3b | 2013-07-30 | 2013-07-31 | 23:35 | 0:25 | STOP SAMI, White Label, Home Connections, Tools Front-End and Scheduling applications. (DONE IN PARALLEL) (Concurrent with 3a) (Notify ASM BEAST Mobile Support Team as each application is stopped to allow them to validate immediately after, SYNCHRONIZED with step 3c) | ASM INFRA Team (NEED MULTIPLE ADMINS) | 50 minutes
3c | 2013-07-30 | 2013-07-31 | 23:35 | 0:25 | VALIDATE SAMI, WhiteLabel, Home Connections, Tools Front-End, and Scheduling are stopped. (Work alongside ASM Infra Team as they stop each application, perform validation immediately afterwards that application is stopped, SYNCHRONIZED with step 3b) | ASM BEAST Mobile Support Team | 50 minutes
4 | 2013-07-31 | 2013-07-31 | 0:25 | 1:10 | STOP all Oracle and MySQL on DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB) (DONE IN PARALLEL ON EACH DB SERVER) | Database Team | 45 minutes
5 | 2013-07-31 | 2013-07-31 | 1:10 | 2:00 | Begin RHEL 5 patching physical servers and manually apply Oracle ASM LIB RPM previously provided by Oracle DB Team in step 1 on DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB) (SERVERS DONE IN PARALLEL) | Unix Team | 50 minutes
6 | 2013-07-31 | 2013-07-31 | 2:00 | 2:30 | REBOOT servers and validate physical servers on DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB) (SERVERS DONE IN PARALLEL) | Unix Team | 30 minutes
7a | 2013-07-31 | 2013-07-31 | 2:30 | 3:05 | VERIFY the Oracle ASM LIB and Disk integrity (done on all servers in parallel) DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB), (CONCURRENT with 7b) | Database Team | 35 Minutes
7b | 2013-07-31 | 2013-07-31 | 2:30 | 3:05 | CONFIGURE MyHR Oracle RAC database services / rebalanced and active on all 3 nodes for DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB) (DONE IN PARALLEL ON EACH SERVER) (CONCURRENT with 7a) | Gopesh Paneri | 35 Minutes
8a | 2013-07-31 | 2013-07-31 | 3:05 | 3:45 | VALIDATE that Oracle RAC, Protegrity Clients and MySQL are running on DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB). (DONE IN PARALLEL ON EACH CLUSTER) (CONCURRENT with 8b) | Database Team | 40 Minutes
8b | 2013-07-31 | 2013-07-31 | 3:05 | 3:45 | Configure MyHR Oracle RAC database services / rebalanced across all 3 nodes for DB CLUSTER (DLP20XDB DLP21XDB DLP22XDB) (DONE IN PARALLEL ON EACH CLUSTER) (CONCURRENT with 8a) | Gopesh Paneri | 40 minutes
9a | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | START BBFB and validate that application is running. (CONCURRENT with 9b 9c 9d) | BBFB Team | 55 minutes
9b | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | START SAMI, White Label, Home Connections and Tools Front-End applications. (APPS STARTED IN PARALLEL) (Notify ASM BEAST Mobile Support Team as each application is started to allow them to validate immediately after, SYNCHRONIZED with step 9c, CONCURRENT with 9a 9d) | ASM INFRA Team (NEED MULTIPLE ADMINS) | 55 minutes
9c | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | VALIDATE if SAMI, White Label, Home Connections and Tools Front-End applications are running. (Work alongside ASM Infra Team as they start each application, perform validation immediately afterwards that application is started, SYNCHRONIZED with step 9b, CONCURRENT with 9a 9d) | ASM BEAST Mobile Support Team | 55 minutes
9d | 2013-07-31 | 2013-07-31 | 3:45 | 4:40 | VALIDATE MyHR and TLC applications are running correctly. They should automatically reconnect to the Oracle database when it is back online. (CONCURRENT with 9a 9b 9c) (Unix Team / MyHR: Click on "Apps that Reconnect" Tab in spreadsheet and following directions for MyHR validation, escalate to Balaram from MyHR in Contact Info Tab if there is an issue) | TLC / Unix Team assisting MyHR | 55 minutes
10a | 2013-07-31 | 2013-07-31 | 4:40 | 5:00 | START monitoring and alerting of all Servers DB CLUSTER 1 (DLP20XDB DLP21XDB DLP22XDB), (SERVERS DONE IN PARALLEL) (CONCURRENT with 10b) | ESM Team | 20 minutes
10b | 2013-07-31 | 2013-07-31 | 4:40 | 5:00 | TLC JOBS: Set Limit of the TLC workstion P01WBMS01 (aka server DLP68UTIL) to 90. (CONCURRENT with 10a) | Data Center Ops OFF-SHORE / TLC Team | 20 minutes
Milestone 1: BBfB / MyHR / TLC / WhiteLabel / SAMI / Home Connections / Scheduling / Tools Front-End |  | 2013-07-31 |  | 7:45 | DB CLUSTER SERVERS, DLP20XDB, DLP21XDB, DLP22XDB, are PCI PATCHED |  | 0 minute buffer

## PROD pdl01gendb023 DAY 2
Milestones | Start Date | End Date | ETS (CST) | ETC (CST) | Activity | Team Responsible for the Changes | Est. Time Needed | OWNER | Actual Time Started | Actual Time Completed | Delays Experienced / Comments | Notes
DAY BEFORE STEPS |  |  |  |  | Take one-off full system backup , retention of 7 days | Backup Team
[5 empty] | Ensure database backup is good | Database Team
[5 empty] | Ensure / 400 and /var has 200 MB free space | Unix Team
PRE-DEPLOYMENT STEPS | 2017-05-08 | 2017-05-08 | 14:00 | 15:00 | PROD DB CLUSTER ORACLE RAC Servers in-Scope: pdl01gendb023)
0 | 2017-05-08 | 2017-05-08 | 14:00 | 15:00 | Load the Retek RTKOUT6 calendar | Maestro Team | 60 minutes | L2-TWS-IT-US
PATCH DEPLOYMENT STEPS | 2017-05-09 | 2017-05-09 | 4:05 | 9:45 | PROD DB CLUSTER ORACLE RAC Servers in-Scope: pdl01gendb023)
1a.a | 2017-05-09 | 2017-05-09 | 4:05 | 4:10 | If any background jobs/process owned by rtkbatch user found needs to be killed at Unix level in DXP22/23HXA (Capture the snapshot of the jobs before killing if any) | RMS Support Team | 5 minutes | L2-ASM-RETEK-IT-US
1a.b | 2017-05-09 | 2017-05-09 | 4:10 | 4:20 | Killing the batch/job processes: a. DB level - RMS support to provide SID, SERIAL details to Oracle Apps DB team for killing in DB backend. b. OS level - If batch session is not connected to DB, RMS support to proceed in killing the session in OS level in Unix. | RMS Support Team / Oracle Apps Team | 10 minutes | L2-ASM-RETEK-IT-US / L2-DB-ORACLE-APPS-IT-GLB
1b | 2017-05-09 | 2017-05-09 | 4:05 | 4:20 | STOP monitoring and alerting of all Servers PROD DB CLUSTER pdl01gendb023 ) . Refer the tab Probes for more details | Event Management team | 15 minutes | L1-MEM-IT-GLB | concurrent with 1a
2a | 2017-05-09 | 2017-05-09 | 4:20 | 4:25 | Relocate all Retek database services back to pdl01gendb022 using script "Day1postPCI_prod" and "Day2Pre Note: Script can be run from any location in pdl01gendb023 | L2-Oracle-AppsDBA-Support | 5 minutes | L2-DB-ORACLE-APPS-IT-GLB
2b | 2017-05-09 | 2017-05-09 | 4:25 | 4:35 | Validate all the Retek database services should be running on pdl01gendb022 Command: ostat -s op01rtdb | L2-Oracle-AppsDBA-Support | 10 minutes | L2-DB-ORACLE-APPS-IT-GLB
3a | 2017-05-09 | 2017-05-09 | 4:35 | 4:50 | Recycle the inventory management App Pool - One Server at a time pdw04b49ap001 pdw04b49ap002 pdw04b49ap003 pdw01b50ap01a pdw01b50ap02a pdw01b50ap02b | Layer 7 Team | 15 minutes | L2-MW-SOA-IT-GLB
3b |  |  | 4:35 | 4:50 | Apptalk needs to recycle all Real time adapters that are connecting to RETEK DB (RESA interface) | Apptalk Team | 15 minutes | L2-APPTALK
4a | 2017-05-09 | 2017-05-09 | 4:35 | 5:05 | Application team to validate their online screens are up and Manually run a test job in the backend. Confirm with the OMS team that OMS webservice is also running normally. | RMS Support Team | 30 minutes | L2-ASM-RETEK-IT-US
4b | 2017-05-09 | 2017-05-09 | 4:35 | 5:05 | All RSS containers need to be bounced one server at a time (Only if errors encountered while validating RSS) | L2-Oracle-AppsDBA-Support | 30 minutes | L2-DB-ORACLE-APPS-IT-GLB
4c | 2017-05-09 | 2017-05-09 | 4:35 | 5:05 | OMS Services need to be recycled only if RMS connectivity errors encountered, one server at a time | ASM Infra, Layer 7 and OMS Support Team | 30 minutes | L2-MW-APP-IT-GLB L2-ASM-OMS-IT-US
5b | 2017-05-09 | 2017-05-09 | 5:05 | 5:25 | Set the Limit for P01RTMS01 back to 30 Monitor whether batches are completing without failure | Datacenter Team | 20 minutes | L2-DATACENTER-OPS-IT-GLB
6a | 2017-05-09 | 2017-05-09 | 5:25 | 5:40 | If there were no issues encountered with the batch, set the limit back to 90. | Datacenter Team | 15 minutes | L2-DATACENTER-OPS-IT-GLB | 4b, 4c and 5a can be done in parallel
6b | 2017-05-09 | 2017-05-09 | 5:25 | 5:40 | If there were no issues encountered with the batch, rerun the jobs killed at step 1.b | RMS Support Team | 15 minutes | L2-ASM-RETEK-IT-US
7a | 2017-05-09 | 2017-05-09 | 5:05 | 5:25 | DOWNLOAD RPM's for Oracle ASM LIB to DB CLUSTER pdl01gendb023). Database Team to communicate location of RPM package to UNIX Team (UNIX team will manually install Oracle ASM LIB RPM when applying patches in step 6). (CONCURRENT with 1b 1c 1d) | Database Team / Unix Team | 20 minutes | DBA Team / L2 Unix | Please doble check if there is any job running in DLP24DB
7b | 2017-05-09 | 2017-05-09 | 5:05 | 5:25 | BACKUP server configuration of all servers (CONCURRENT with 1a 1c 1d) PROD DB CLUSTER pdl01gendb023) | Unix Team | 20 minutes | L2 Unix
7c |  |  | 5:05 | 5:35 | Stop NEW RSS instance on PDL01RSSWB01B, PDL01RSSWB02B and PDL01RSSAP01B and PDL01RSSAP02B Stop REIM Services on PDL01RM1WB01C | Appserver team | 30 minutes | L2-MW-APP-IT-GLB
7c | 2017-05-09 | 2017-05-09 | 5:05 | 5:35 | STOP Oracle database instance, VIPs and the Oracle Clusterware Services, VALIDATE status of ASM Disk Groups on PROD DB CLUSTER pdl01gendb023) Disable crs on pdl01gendb023 | Database Team | 30 minutes | L2-DB-ORACLE-IT-US
8 | 2017-05-09 | 2017-05-09 | 5:35 | 6:35 | START PATCHING physical servers on DB CLUSTER ( pdl01gendb023) and Linux app servers PDL01RM1WB01C pdl01u26ap01a pdl01u26ap01b PDL01RSSWB01B PDL01RSSWB02B PDL01RSSAP02B PDL01RSSAP01B | Unix Team | 60 minutes | L2-PLT-UNIX-IT-US
9 | 2017-05-09 | 2017-05-09 | 6:35 | 6:45 | VALIDATE OS is running fine, | Unix Team | 10 minutes | L2-PLT-UNIX-IT-US
10 | 2017-05-09 | 2017-05-09 | 6:45 | 7:45 | REBOOT servers and VALIDATE physical servers on DB CLUSTER pdl01gendb023) | Unix Team | 60 minutes | L2-PLT-UNIX-IT-US
11a | 2017-05-09 | 2017-05-09 | 7:45 | 9:00 | Enable crs in pdl01gendb023 and relink Oracle grid binaries Relink Oracle Home | Database Team | 75 minutes | L2-DB-ORACLE-IT-US
11b |  |  | 7:45 | 9:00 | Start NEW RSS instance on PDL01RSSWB01B, PDL01RSSWB02B and PDL01RSSAP01B and PDL01RSSAP02B Start REIM Services on PDL01RM1WB01C
12 | 2017-05-09 | 2017-05-09 | 9:00 | 9:30 | START / VALIDATE ASM Disk Groups are mounted. VALIDATE Oracle Clusterware, Oracle database instances and VIP services have started (done via /etc/inittab) on DB CLUSTER pdl01gendb023 ) Note: Do not relocate Retek Services back to pdl01gendb023 | Database Team | 30 minutes | L2-Oracle-Support | Confirm with OMS team if the web service required to be bounced after the PCI Patching ( If so than Layer7 team can do that )
12a | 2017-05-09 | 2017-05-09 | 9:30 | 9:45 | START SERVER monitoring and alerting pdl01gendb023 | ESM Team | 15 minutes | L1-MEM-IT-GLB
Milestone 1: PROD DB Cluster RETEK / Oracle EBS / Discover | 2017-05-09 | 2017-05-09 | 4:05 | 9:45 | PROD DB CLUSTER SERVERS, pdl01gendb023 are updated with latest Patches

## PROD DLP24DB DAY 2-OLD (hidden)
Milestones | Start Date | End Date | ETS (CST) | ETC (CST) | Activity | Team Responsible for the Changes | Est. Time Needed | Status | Actual Time Started | Actual Time Completed | Delays Experienced / Comments | Notes
DAY BEFORE STEPS |  |  |  |  | Take one-off full system backup , retention of 7 days | Backup Team
[5 empty] | Ensure database backup is good | Database Team
[5 empty] | Ensure / 400 and /var has 200 MB free space | Unix Team
Pre-Deployment Steps | 2017-05-09 | 2017-05-09 | 4:00 |  | PROD DB CLUSTER ORACLE RAC Servers in-Scope: (DLP24DB)
1a | 2017-05-09 | 2017-05-09 | 4:00 | 4:15 | Set the Limit for RESA Jobs to 0 after DATEFLIP job is completed (List of jobs - ??) | RESA Team | 15 minutes | L2-ASM-RESA-ITGLB
1b | 2017-05-09 | 2017-05-09 | 4:00 | 4:15 | If any background jobs/process owned by rtkbatch user found needs to be killed at Unix level in DXP22/23HXA (Capture the snapshot of the jobs before killing if any) | Oracle Apps Team | 15 minutes | L2-DB-ORACLE-APPS-IT-GLB
2a | 2017-05-09 | 2017-05-09 | 4:15 | 4:30 | STOP monitoring and alerting of all Servers (CONCURRENT with 2b 2c 2d 2e 2f 2g) PROD DB CLUSTER (DLP24DB ) . | Event Management team | 15 minutes | L1-MEM-IT-GLB
2b | 2017-05-09 | 2017-05-09 | 4:15 | 4:30 | STOP the realtime adapters STH to RESA (CONCURRENT with 2a 2c 2d 2e 2f 2g) | Apptalk | 15 minutes | L2-APPTALK-IT-GLB
2c | 2017-05-09 | 2017-05-09 | 4:15 | 4:30 | DOWNLOAD RPM's for Oracle ASM LIB to DB CLUSTER (DLP24DB). Database Team to communicate location of RPM package to UNIX Team (UNIX team will manually install Oracle ASM LIB RPM when applying patches in step 6). (CONCURRENT with 2a 2b 2d 2e 2f 2g) | Database Team / Unix Team | 15 minutes | DBA Team / L2 Unix
2d | 2017-05-09 | 2017-05-09 | 4:15 | 4:30 | BACKUP server configuration of all servers (CONCURRENT with 1a 1c 1d) PROD DB CLUSTER (DLP24DB) | Unix Team | 15 minutes | L2 Unix
2e | 2017-05-09 | 2017-05-09 | 4:15 | 4:30 | Turnoff RTK & HP service Guard Monitoring (CONCURRENT with 2a 2b 2c 2d 2e 2g) | L2-Oracle-AppsDBA-Support | 15 minutes | L2-DB-ORACLE-APPS-IT-GLB
2f | 2017-05-09 | 2017-05-09 | 4:15 | 4:30 | Send Mail to AppTalk Impacts about the patching activity | Apptalk | 15 minutes | L2-APPTALK-IT-GLB
2g | 2017-05-09 | 2017-05-09 | 4:15 | 4:30 | Stop All the AppTalk Custom Monitors in BSM | Event Management team | 15 minutes | L1-MEM-IT-GLB
3a | 2017-05-09 | 2017-05-09 | 4:30 | 4:45 | Relocate services using script "Day2prePCI_prod" from DLP23DB Script can be run from any location | L2-Oracle-AppsDBA-Support | 15 minutes | L2-DB-ORACLE-APPS-IT-GLB
3b | 2017-05-09 | 2017-05-09 | 4:45 | 5:00 | RESA team to test one sample job after relocation. On successful, release the jobs | RESA Team | 15 minutes | L2-ASM-RESA-ITGLB
4.a | 2017-05-09 | 2017-05-09 | 5:00 | 5:15 | Application team to validate their applications and batch jobs are running fine | RMS Support Team / RESA | 15 minutes | L2-ASM-RETEK-IT-US
4.b | 2017-05-08 | 2017-05-08 | 5:00 | 5:15 | If there were no issues encountered with the batch, rerun the jobs killed at step 1.b | RMS Support Team / RESA | 15 minutes | L2-ASM-RETEK-IT-US
5a | 2017-05-09 | 2017-05-09 | 5:15 | 5:45 | Gracefully shutdown Oracle Streams (Capture,Propagation and apply Process) on DLP24DB servers. Comment or Hold the archive backup job to prevent archive log deletion. When outage is over archivelogs needs to be applied on streams to bring in SYNC THIS IS VERY CRITICAL TASK | Database Team | 30 minutes | L2-DB-ORACLE-IT-US
5b | 2017-05-09 | 2017-05-09 | 5:15 | 5:45 | STOP Oracle databases, VIPs and the Oracle Clusterware Services, VALIDATE status of ASM Disk Groups on PROD DB CLUSTER (DLP24DB) Disable crs on DLP24DB | Database Team | 30 minutes | L2-DB-ORACLE-IT-US
6 | 2017-05-09 | 2017-05-09 | 5:45 | 6:45 | START PATCHING RHEL 5 physical servers on DB CLUSTER ( DLP24DB) | Unix Team | 60 minutes | L2-PLT-UNIX-IT-US
7 | 2017-05-09 | 2017-05-09 | 6:45 | 7:00 | VALIDATE OS is running fine, | Unix Team | 15 minutes | L2-PLT-UNIX-IT-US
8 | 2017-05-09 | 2017-05-09 | 7:00 | 8:00 | REBOOT servers and VALIDATE physical servers on DB CLUSTER (DLP24DB) | Unix Team | 60 minutes | L2-PLT-UNIX-IT-US
9 | 2017-05-09 | 2017-05-09 | 8:00 | 9:15 | Enable crs in DLP24DB and relink Oracle grid binaries Relink Oracle Home | Database Team | 75 minutes | L2-DB-ORACLE-IT-US
10 | 2017-05-09 | 2017-05-09 | 9:15 | 9:45 | START / VALIDATE ASM Disk Groups are mounted. VALIDATE Oracle Clusterware, Oracle databases and VIP services have started (done via /etc/inittab) on DB CLUSTER (DLP24DB ) | Database Team | 30 minutes | L2-Oracle-Support
11.a | 2017-05-09 | 2017-05-09 | 9:45 | 10:00 | Set the Limit for RESA Jobs to 0 | RESA Team | 15 minutes | L2-ASM-RESA-ITGLB
11.b | 2017-05-08 | 2017-05-08 | 9:45 | 10:00 | If any background jobs/process owned by rtkbatch user found needs to be killed at Unix level | L2-Oracle-AppsDBA-Support | 15 minutes | L2-DB-ORACLE-APPS-IT-GLB
12 | 2017-05-09 | 2017-05-09 | 10:00 | 10:15 | Relocate services using script "Day2postPCI_prod" from DLP23DB | Database Team | 15 minutes | L2-Oracle-Support
13 | 2017-05-09 | 2017-05-09 | 10:00 | 10:15 | Start Oracle Streams (Capture,Propagation and apply Process) on DLP24DB Server and check if streams streams working as expeted and in SYNC. You many need to delete archvie logs manually that are already applied on streams THIS IS VERY CRITICAL TASK | Database Team | 15 Minutes | L2-Oracle-Support
14 | 2017-05-09 | 2017-05-09 | 10:15 | 10:30 | RESA team to test one sample job after relocation. On successful, release the jobs | RESA Team | 15 minutes | L2-DATACENTER-OPS-IT-GLB
15 | 2017-05-08 | 2017-05-08 | 10:15 | 10:30 | If there were no issues encountered with the batch, rerun the jobs killed at step 11.b | RMS Support Team / RESA | 15 minutes | L2-ASM-RETEK-IT-US
16 | 2017-05-09 | 2017-05-09 | 10:30 | 10:45 | Bring UP and Validate the AppTalk Adapters | Apptalk | 15 minutes | L2-APPTALK-IT-GLB
17 | 2017-05-09 | 2017-05-09 | 10:45 | 11:00 | Start All the AppTalk Custom Monitors in BSM | ESM Team | 15 minutes | L3-ESM-IT-GLB
18a | 2017-05-09 | 2017-05-09 | 11:00 | 11:15 | START monitoring and alerting of all servers in (CONCURRENT with 11b 11c ) PROD DB CLUSTER (DLP24DB) | ESM Team | 15 minutes | L1-MEM-IT-GLB
18b | 2017-05-09 | 2017-05-09 | 11:00 | 11:15 | START the Monitoring for RTK & HP service Guard Monitoring (CONCURRENT with 11a 11c) | L2-Oracle-AppsDBA-Support | 15 minutes | L2-DB-ORACLE-APPS-IT-GLB
Milestone 1: PROD DB Cluster RETEK / Oracle EBS / Discover | 2017-05-09 | 2017-05-09 |  | 11:15 | PROD DB CLUSTER SERVERS, DLP24DB are updated with latest Patches

## PROD Relocation DAY 3
Milestones | Start Date | End Date | ETS (CST) | ETC (CST) | Activity | Team Responsible for the Changes | Est. Time Needed | Service Now Group | Status | Actual Time Started | Actual Time Completed | Delays Experienced / Comments | Notes
Day Before Steps |  |  |  |  | Ensure good full backup is available for these Servers | Storage & Backup Team
[5 empty] | Ensure good DB backup available for databases on these Servers | Database Team
[5 empty] | Ensure all Kernel, OracleASM and driver/firmware packages available | Unix Team
Pre-Deployment Steps | 2017-05-09 | 2017-05-09 | 14:00 | 15:00 | PROD DB CLUSTER ORACLE RAC Servers in-Scope: pdl01gendb023
0 | 2017-05-09 | 2017-05-09 | 14:00 | 15:00 | Load the Retek RTKOUT6 calendar | Maestro Team | 60 minutes | L2-TWS-IT-US
PATCH DEPLOYMENT STEPS | 2017-05-10 | 2017-05-10 | 4:05 | 10:20 | PROD DB CLUSTER ORACLE RAC Servers in-Scope:
1a.a | 2017-05-10 | 2017-05-10 | 4:05 | 4:10 | If any background jobs/process owned by rtkbatch user found needs to be killed at Unix level in DXP22/23HXA (Capture the snapshot of the jobs before killing if any) | RMS Support Team | 5 minutes | L2-ASM-RETEK-IT-US
1a.b | 2017-05-10 | 2017-05-10 | 4:10 | 4:20 | Killing the batch/job processes: a. DB level - RMS support to provide SID, SERIAL details to Oracle Apps DB team for killing in DB backend. b. OS level - If batch session is not connected to DB, RMS support to proceed in killing the session in OS level in Unix. | RMS Support Team / Oracle Apps Team | 10 minutes | L2-ASM-RETEK-IT-US / L2-DB-ORACLE-APPS-IT-GLB
2a | 2017-05-10 | 2017-05-10 | 4:20 | 4:30 | Relocate Retek services back to pdl01gendb023 using script "Day2postPCI_prod" Note: Script can be run from any location in pdl01gendb023/22 | L2-Oracle-DBA-Support | 10 minutes | L2-DB-ORACLE-APPS-IT-GLB
2a | 2017-05-10 | 2017-05-10 | 4:30 | 4:35 | Validate most of the Retek services should be running on pdl01gendb022 and pdl01gendb023 Command: ostat -s op01rtdb | L2-Oracle-DBA-Support | 5 minutes | L2-DB-ORACLE-APPS-IT-GLB
3 |  |  | 4:20 | 4:35 | Unix team to patch pdl01msgut001 and PDL01RM1AP01C (For PDL01RM1AP01C please confirm if RSSU0003 is completed before patching the server - RSS Support will confirm) | Unix Team | 20 Mins | L2-PLT-LINUX-IT-US
4a |  |  | 4:35 | 4:50 | Apptalk needs to recycle all Real time adapters that are connecting to RETEK DB (RESA interface) | Apptalk Team | 15 minutes | L2-APPTALK
4b |  |  | 4:35 | 4:50 | Validate if CyberArk Vault is started for PDL01RM1AP01C
4b | 2017-05-10 | 2017-05-10 | 4:35 | 5:05 | Application team to validate their online screens are up and Manually run a test job in the backend. Confirm with the OMS team that OMS webservice is also running normally. | RMS Support Team | 30 minutes | L2-ASM-RETEK-IT-US
4c | 2017-05-10 | 2017-05-10 | 4:35 | 5:05 | All RSS containers need to be bounced one server at a time (Only if errors encountered while validating RSS) | L2-Oracle-AppsDBA-Support | 30 minutes | L2-DB-ORACLE-APPS-IT-GLB
4d | 2017-05-10 | 2017-05-10 | 4:35 | 5:05 | OMS Services need to be recycled only if RMS connectivity errors encountered, one server at a time | ASM Infra, Layer 7 and OMS Support Team | 30 minutes | L2-MW-APP-IT-GLB L2-ASM-OMS-IT-US
5b | 2017-05-10 | 2017-05-10 | 5:05 | 5:25 | Set the Limit for P01RTMS01 back to 30 Monitor whether batches are completing without failure | Datacenter Team | 20 minutes | L2-DATACENTER-OPS-IT-GLB
6a | 2017-05-10 | 2017-05-10 | 5:25 | 5:40 | If there were no issues encountered with the batch, set the limit back to 90. | Datacenter Team | 15 minutes | L2-DATACENTER-OPS-IT-GLB | 4b, 4c and 5a can be done in parallel
6b | 2017-05-10 | 2017-05-10 | 5:25 | 5:40 | If there were no issues encountered with the batch, rerun the jobs killed at step 1.b | RMS Support Team | 15 minutes | L2-ASM-RETEK-IT-US
15 | 2017-05-10 | 2017-05-10 | 9:30 | 9:50 | START ORACLE Retek Application (ARI Notification server) | L2-Oracle-AppsDBA-Support | 20 minutes | L2-DB-ORACLE-APP-IT-GLB
16 | 2017-05-10 | 2017-05-10 | 9:50 | 10:05 | START the Maestro batch for PROD DB SERVER ON ARI Notification Batch JOB | Data Center Ops | 15 minutes | L2-DATACENTER-OPS-IT-GLB
17a | 2017-05-10 | 2017-05-10 | 10:05 | 10:20 | VALIDATION of ARI Application status | IS -Retek RMS support | 15 minutes | L2-ASM-Retek-IT-US
17b | 2017-05-10 | 2017-05-10 | 10:05 | 10:20 | START monitoring and alerting of all servers in PROD DB SERVER (CONCURRENT with 10a) | Event Management team | 15 minutes | L1-MEM-IT-GLB

## Probes
Day 2

## Contact
Application | Roll Call | Phone Number | Escalation Contact | Contact DL | Service Now Group
BBY Infrastructure - Platform Services - Linux | Andrea Rucks | (612) 812-4698 | Yes | *IT Platform Services | L2-PLT-LINUX
L2 Unix Team | Naincy Katiyar | (612) 849-5658 | onsite | L2 Unix Team | L2-PLT-LINUX-US
L2 Unix Team | Sekhar Pulipati | (612) 806-8353 | onsite | L2 Unix Team | L2-PLT-LINUX-US
BBY Infrastructure Service Manager | Joe Arko | (612) 306-6293 | Yes | joseph.arko@bestbuy.com
BBY Service Manager | Brenda Mccan | 612-802-5920 | Yes
Retek Escalation | Lynn Cannama/Alex | 651-202-7528/ 612-562-2237 | Yes
RMS | RMS Support | +63-917-804-9975 | Oncall | *IS - RETEK Staff | L2-ASM-RETEK-IT-US
ReSA/ReIM | Resa Support | 91-9886928729/91-9611026688 | Oncall | *ReSA Support Group | L2-ASM-RESA-IT-GLB
TCS Oracle Database | Nukesh Bhoyar | (612) 812-2789 | Yes | L2-Oracle-Support | L2-DB-ORACLE-IT-US
DC OPS ON-SHORE | Mohit Kumar | 516-453-5736 (24/7 On-call Batch Ops) | Mohit | DataCenter@bestbuy.com | L2-DATACENTER-OPS-IT-GLB

## PRD DLP33-34DB DLP20-21-22XDB (hidden)
Milestones | Start Date | End Date | ETS (CST) | ETC (CST) | Activity | Team Responsible for the Changes | Est. Time Needed | Status | Actual Time Started | Actual Time Completed | Delays Experienced / Comments | Notes
DAY BEFORE STEPS |  |  |  |  | Take one-off full system backup on 7/27, retention of 7 days | Backup Team
[5 empty] | Ensure database backup is good on 7/27 | Database Team
[5 empty] | Ensure /var has 650 MB free space | Unix Team
Pre-Deployment Steps | 2013-07-28 | 2013-07-29 | 11:00 | 6:45 | RHEL 5 ORACLE RAC and MySQLServers in-Scope for Group 1 PCI PROD patching: DB CLUSTER 1 - BBfB / MyHR / TLC / WhiteLabel / SAMI / Home Connections (DLP20XDB DLP21XDB DLP22XDB), DB CLUSTER 2 - EJ / ESC / Missing Trans. App. (DLP33DB DLP34DB)
1a | 2013-07-28 | 2013-07-29 | 11:00 | 11:30 | Stop monitoring and alerting of all Servers (CONCURRENT with 1b 1c 1d 1e 1f) DB CLUSTER 1 (DLP20XDB DLP21XDB DLP22XDB), DB CLUSTER 2 (DLP33DB DLP34DB) (servers done in parallel). BEAST Mobile Support Team to provide ESM Team with list of Monitoring Probes scheduled for maintenance. | ESM Team | 30 minutes
1b | 2013-07-28 | 2013-07-29 | 11:00 | 11:30 | Take server configuration backup of all GROUP 1 Servers (CONCURRENT with 1a 1c 1d 1e 1f) DB CLUSTER 1 (DLP20XDB DLP21XDB DLP22XDB), DB CLUSTER 2 (DLP33DB DLP34DB) (servers done in parallel) | Unix Team | 30 minutes
1c | 2013-07-28 | 2013-07-29 | 11:00 | 11:30 | TLC JOBS: Set Limit of the TLC workstion P01WBMS01 (aka server DLP68UTIL) to 0. Cancel the job stream P02INMS01#WBNLD097 only after the confirmation via TLC support team. (CONCURRENT with 1a 1b 1d 1e 1f) | Data Center Ops OFF-SHORE / TLC Team | 30 minutes
1d | 2013-07-28 | 2013-07-29 | 11:00 | 11:30 | MISSING TRANSACTION APPS US JOB: Set Priority of Jobstream DS01CDS#EEJND001 to 0. (CONCURRENT with 1a 1b 1c 1e 1f) | Data Center Ops OFF-SHORE | 30 minutes
1e | 2013-07-28 | 2013-07-29 | 11:00 | 11:30 | MISSING TRANSACTION APPS CANADA JOB: Set Priority of Jobstream "394_Missing TranBatchSchedule" to 0. (CONCURRENT with 1a 1b 1c 1d 1f) | Data Center Ops ON-SHORE | 30 minutes
1f | 2013-07-28 | 2013-07-29 | 11:00 | 11:30 | Download RPM's for ASM LIB to DB CLUSTER 1 (DLP20XDB DLP21XDB DLP22XDB), DB CLUSTER 2 (DLP33DB DLP34DB). Database Team to communicate location of RPM package to UNIX Team (UNIX team will manually install Oracle ASM LIB RPM when applying patches in step 6). (CONCURRENT with 1a 1b 1c 1d 1e). | Database Team | 30 minutes
2a | 2013-07-28 | 2013-07-29 | 11:30 | 0:00 | VALIDATE that no application batch jobs are running and cancel jobs if they are (ALL APPLICATIONS DONE IN PARALLEL) (Concurrent with 2b) | DC Ops | 30 minutes
2b | 2013-07-28 | 2013-07-29 | 11:30 | 0:00 | Stop AppTalk adapters (in parallel) for EJ / ESC for DB CLUSTER 2 (DLP33DB DLP34DB) (Concurrent with 2a) | AppTalk | 30 minutes
3a | 2013-07-29 | 2013-07-29 | 0:00 | 0:45 | Stop BBFB and validate that application is down. (DONE IN PARALLEL) (Concurrent with 3b) | BBFB Team | 45 minutes
3b | 2013-07-29 | 2013-07-29 | 0:00 | 0:45 | Stop SAMI, White Label, Home Connections and Tools Front-End applications. (DONE IN PARALLEL) (Concurrent with 3a) (Notify ASM BEAST Mobile Support Team as each application is stopped to allow them to validate sooner) | ASM INFRA Team | 45 minutes
4 | 2013-07-29 | 2013-07-29 | 0:45 | 1:15 | VALIDATE if SAMI / Home Connections / Tools Front-End / and Scheduling are stopped. (validate in parallel) | ASM BEAST Mobile Support Team | 30 minutes
5 | 2013-07-29 | 2013-07-29 | 1:15 | 2:00 | Stop all Oracle and MySQL on DB CLUSTER 1 and Oracle on DB CLUSTER 2, (DONE IN PARALLEL ON EACH DB CLUSTER) | Database Team | 45 minutes
6 | 2013-07-29 | 2013-07-29 | 2:00 | 3:00 | Begin RHEL 5 patching physical servers and manually apply Oracle ASM LIB RPM previously provided by Oracle DB Team (servers done in parallel): DB CLUSTER 1 (DLP20XDB DLP21XDB DLP22XDB), DB CLUSTER 2 (DLP33DB DLP34DB) | Unix Team | 60 minutes
7 | 2013-07-29 | 2013-07-29 | 3:00 | 3:30 | Server reboot and validate physical servers (in parallel): DB CLUSTER 1 (DLP20XDB DLP21XDB DLP22XDB), DB CLUSTER 2 (DLP33DB DLP34DB) | Unix Team | 30 minutes
8a | 2013-07-29 | 2013-07-29 | 3:30 | 4:30 | VERIFY the Oracle ASM LIB and Disk integrity (done on all servers in parallel) DB CLUSTER 1 (DLP20XDB DLP21XDB DLP22XDB), DB CLUSTER 2 (DLP33DB DLP34DB) (CONCURRENT with 8b) | Database Team | 45 Minutes
8b | 2013-07-29 | 2013-07-29 | 3:30 | 4:30 | Configure MyHR Oracle RAC database services / rebalanced and active on all 3 nodes for DB CLUSTER 1 (DLP20XDB DLP21XDB DLP22XDB) (DONE IN PARALLEL ON EACH CLUSTER) (CONCURRENT with 8a) | Gopesh Paneri | 45 Minutes
9a | 2013-07-29 | 2013-07-29 | 4:30 | 5:30 | VALIDATE that Oracle RAC, Protegrity Clients and MySQL are running on DB CLUSTER 1 and VALIDATE Oracle, Protegrity Clients are running on DB CLUSTER 2. (DONE IN PARALLEL ON EACH CLUSTER) (CONCURRENT with 9b) | Database Team | 60 Minutes
9b | 2013-07-29 | 2013-07-29 | 4:30 | 5:30 | Configure MyHR Oracle RAC database services / rebalanced and active on all 3 nodes for DB CLUSTER 1 (DLP20XDB DLP21XDB DLP22XDB) (DONE IN PARALLEL ON EACH CLUSTER) (CONCURRENT with 9a) | Gopesh Paneri | 60 minutes
10a | 2013-07-29 | 2013-07-29 | 5:30 | 6:15 | Start BBFB and validate that application is running. (DONE IN PARALLEL) (Concurrent with 10b) | BBFB Team | 45 minutes
10b | 2013-07-29 | 2013-07-29 | 5:30 | 6:15 | Start SAMI, White Label, Home Connections and Tools Front-End applications. (DONE IN PARALLEL) (Concurrent with 10a) (Notify ASM BEAST Mobile Support Team as each application is started to allow them to validate sooner) | ASM INFRA Team | 45 minutes
11 | 2013-07-29 | 2013-07-29 | 6:15 | 6:45 | VALIDATE if SAMI / Home Connections / Tools Front-End / and Scheduling are started. (Validate in parallel) | ASM BEAST Mobile Support Team | 30 minutes
12a | 2013-07-29 | 2013-07-29 | 7:15 | 7:45 | Start monitoring and alerting of all Servers DB CLUSTER 1 (DLP20XDB DLP21XDB DLP22XDB), DB CLUSTER 2 (DLP33DB DLP34DB) (servers done in parallel) (CONCURRENT with 12b 112c 12d) | ESM Team | 30 minutes
12b | 2013-07-29 | 2013-07-29 | 7:15 | 7:45 | TLC JOBS: Set Limit of the TLC workstion P01WBMS01 (aka server DLP68UTIL) to 90. (CONCURRENT with 12a 12c 12d) | Data Center Ops OFF-SHORE / TLC Team | 30 minutes
12c | 2013-07-29 | 2013-07-29 | 7:15 | 7:45 | MISSING TRANSACTION APPS US JOB: Set Priority of Jobstream DS01CDS#EEJND001 to 10. (CONCURRENT with 12a 12b 12d) | Data Center Ops OFF-SHORE | 30 minutes
12d | 2013-07-29 | 2013-07-29 | 7:15 | 7:45 | MISSING TRANSACTION APPS CANADA JOB: Set Priority of Jobstream "394_Missing TranBatchSchedule" to 10. (CONCURRENT with 12a 12b 12c) | Data Center Ops ON-SHORE | 30 minutes
Milestone 1: DB Cluster 1 and DB Cluster 2 Patched | 2013-07-29 | 2013-07-29 |  | 7:45 | DB CLUSTER 1 and DB CLUSTER 2 are PCI PATCHED

## PLDR RLQ33-34DB RLQ35-36XDB (hidden)
Milestones | Start Date | End Date | ETS (CST) | ETC (CST) | Activity | Team Responsible for the Changes | Est. Time Needed | Status | Actual Time Started | Actual Time Completed | Delays Experienced / Comments | Notes
DAY BEFORE STEPS |  |  |  |  | Take one-off full system backup on 7/24, retention of 7 days | Backup Team
[5 empty] | Ensure database backup is good on 7/24 | Database Team
[5 empty] | Ensure /var has 650 MB free space | Unix Team
Pre-Deployment Steps | 2013-07-25 | 2013-07-26 | 11:00 | 5:00 | RHEL 5 ORACLE RAC and MySQLServers in-Scope for Group 1 PCI PLDR patching: DB CLUSTER 1 - BBfB / MyHR / TLC / WhiteLabel / SAMI / Home Connections (RLQ35XDB RLQ36XDB), DB CLUSTER 2 - EJ / ESC / Missing Trans. App. (RLQ33DB RLQ34DB)
1a | 2013-07-25 | 2013-07-26 | 11:00 | 11:30 | Stop monitoring and alerting of all Servers (CONCURRENT with 1b) DB CLUSTER 1(RLQ35XDB and RLQ36XDB) and DB CLUSTER 2 (RLQ33DB and RLQ34DB) (servers done in parallel) | ESM Team | 30 minutes
1b | 2013-07-25 | 2013-07-26 | 11:00 | 11:30 | Take server configuration backup of all GROUP 1 Servers (CONCURRENT with 1a) DB CLUSTER 1(RLQ35XDB and RLQ36XDB) and DB CLUSTER 2 (RLQ33DB and RLQ34DB) (servers done in parallel) | Unix Team | 30 minutes
2a | 2013-07-25 | 2013-07-26 | 11:30 | 0:00 | Validate that no application batch jobs are running and cancel jobs if they are (ALL APPLICATIONS DONE IN PARALLEL) (Concurrent with 2b) | DC Ops | 30 minutes
2b | 2013-07-26 | 2013-07-26 | 11:30 | 0:00 | Stop AppTalk adapters for EJ / ESC for DB CLUSTER 2 (RLQ33DB and RLQ34DB) (Concurrent with 2a) | AppTalk | 30 minutes
3 | 2013-07-26 | 2013-07-26 | 0:00 | 0:45 | Stop all applications that do not reconnect to the database automatically. Applications that can reconnect to the database automatically when it comes back online can stay up. (DONE IN PARALLEL) | Application Teams: (BBfB / TLC / MyHR / WhiteLabel / SAMI / Home Connections / EJ / ESC / Missing Trans. Apps.) | 45 minutes
4 | 2013-07-26 | 2013-07-26 | 0:45 | 1:30 | Stop all Oracle and MySQL on DB CLUSTER 1 and Oracle on DB CLUSTER 2 (DONE IN PARALLEL ON EACH DB CLUSTER) | Database Team | 45 minutes
5 | 2013-07-26 | 2013-07-26 | 1:30 | 2:15 | Begin RHEL 5 patching physical servers (servers done in parallel): RLQ35XDB RLQ36XDB DLQ33DB RLQ34DB | Unix Team | 45 minutes
6 | 2013-07-26 | 2013-07-26 | 2:15 | 2:45 | Server reboot and validate physical servers (in parallel): RLQ35XDB RLQ36XDB DLQ33DB RLQ34DB | Unix Team | 30 minutes
7 | 2013-07-26 | 2013-07-26 | 2:45 | 3:15 | Validate Oracle and MySQL started on DB CLUSTER 1 and validate Oracle started on DB CLUSTER 2 (DONE IN PARALLEL ON EACH CLUSTER) | Database Team | 30 minutes
8 | 2013-07-26 | 2013-07-26 | 3:15 | 4:00 | Start any stopped applications. Perform validation for all applications that database connections are working (DONE IN PARALLEL) | Application Teams: (BBfB / TLC / MyHR / WhiteLabel / SAMI / Home Connections / EJ / ESC / Missing Trans. Apps.) | 45 minutes
9 | 2013-07-29 | 2013-07-29 | 4:00 | 4:30 | Start monitoring and alerting of all Servers DB CLUSTER 1 - BBfB / MyHR / TLC / WhiteLabel / SAMI / Home Connections (RLQ35XDB RLQ36XDB), DB CLUSTER 2 - EJ / ESC / Missing Trans. App. (RLQ33DB RLQ34DB) (servers done in parallel) | ESM Team | 30 minutes
Milestone 1: DB CLUSTER 1 and DB CLUSTER 2 Servers Patched | 2013-07-26 | 2013-07-26 |  | 4:30 | DB CLUSTER 1 and DB CLUSTER 2 are PCI PATCHED

## Sheet1
Team Name | Service Now Name
L2 Unix team | L2-PLT-LINUX-IT-US
L2 DBA team
ESM Team | L3-ESM-IT-GLB
Maestro Team | L2-TWS-IT-US
ASM Infra Oracle Apps | L2-MW-ORA-IT-GLB
AppTalk | L2-APPTALK-IT-GLB
RMS Support Team | L2-ASM-RETEK-IT-US
RESA | L2-ASM-RETEK-IT-US
Data Centre | L2-DATACENTER-OPS-IT-GLB

## schedule
Day 0 | 2017-05-07
Day1 | 2017-05-08
Day2 | 2017-05-09
Day 3 | 2017-05-10
|  | Hostname | Activity | Day | Schedule Date | Schedule Time
|  | pdl01gendb022 | Load the Retek RTKOUT6 calendar | Pre-requisite Step | 2017-05-07 | 14:00 - 16:00
|  | pdl01gendb022 | PCI Patching | Day 1 | 2017-05-08 | 4:05 - 10:00
|  | pdl01gendb023 | Load the Retek RTKOUT6 calendar | Pre-requisite Step | 2017-05-08 | 14:00 - 16:00
|  | pdl01gendb023 | PCI Patching | Day 2 | 2017-05-09 | 4:05 - 10:00
|  | pdl01gendb023 | Load the Retek RTKOUT6 calendar | Pre-requisite Step | 2017-05-09 | 14:00 - 16:00
|  | pdl01gendb023 | Relocation of services back to pdl01gendb023 | Day 3 | 2017-05-10 | 4:05 - 10:00

## Sheet3
Sr.No | Server | Event/Group
1 | pdl01gendb022 | PD Day 1
2 | pdl01gendb023 | PD Day 2